## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Perkins Company | taher nono | 2020-06-19 | 2020-06-24 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION | STATUS | COMMENTS
| Introduction |  | saker |  | 2020-06-20 23:30 | 2020-06-21 15:00 | 13 h | Complete
| Purpose |  | hussien |  | 2020-06-20 23:00 | 2020-06-21 01:00 | 0.083333 | Complete
| Scope of Project |  | hussien |  | 2020-06-21 01:00 | 2020-06-21 03:00 | 0.083333 | Complete
| Glossary |  | saker |  | 2020-06-21 07:00 | 2020-06-21 11:00 | 0.16667 | Complete
| References |  | saker |  | 2020-06-21 11:00 | 2020-06-21 13:00 | 0.083333 | Complete
| FOverview of Document |  | hussien |  | 2020-06-21 13:00 | 2020-06-21 15:00 | 0.083333 | Complete
| Overall Description |  | taher |  | 2020-06-21 16:30 | 2020-06-24 22:30 | 3.25 | Complete
| System Environment |  | taher |  | 2020-06-21 16:30 | 2020-06-22 17:30 | 1.0417 | Complete
| Functional Requirements Specification |  | taher |  | 2020-06-22 17:30 | 2020-06-23 23:30 | 1.25 | Complete
| User Characteristics |  | taher |  | 2020-06-23 23:30 | 2020-06-24 11:30 | 0.5 | Complete
| Non-Functional Requirements |  | taher |  | 2020-06-24 11:30 | 2022-10-02 | 829.5208 | Complete
| Requirements Specification |  | kamel |  | 2020-06-21 15:00 | 2020-06-21 16:30 | 0.0625 | Complete
| External Interface Requirements |  | kamel |  | 2020-06-21 15:00 | 2020-06-21 15:15 | 0.010417 | Complete
| Functional Requirements Specification |  | kamel |  | 2020-06-21 15:15 | 2020-06-21 15:45 | 0.020833 | Complete
| Detailed Non-Functional Requirement |  | kamel |  | 2020-06-21 15:45 | 2020-06-24 22:30 | 3.2812 | Complete
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Perkins Company | taher nono | 2020-06-19 | 2020-06-24 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Introduction |  | saker |  | 2020-06-20 23:30 | 2020-06-21 15:00 | 13 h | Complete
| Purpose |  | hussien |  | 2020-06-20 23:00 | 2020-06-21 01:00 | 0.083333 | Complete
| Scope of Project |  | hussien |  | 2020-06-21 01:00 | 2020-06-21 03:00 | 0.083333 | Complete
| Glossary |  | saker |  | 2020-06-21 07:00 | 2020-06-21 11:00 | 0.16667 | Complete
| References |  | saker |  | 2020-06-21 11:00 | 2020-06-21 13:00 | 0.083333 | Complete
| FOverview of Document |  | hussien |  | 2020-06-21 13:00 | 2020-06-21 15:00 | 0.083333 | Complete
| Overall Description |  | taher |  | 2020-06-21 16:30 | 2020-06-24 22:30 | 3.25 | Complete
| System Environment |  | taher |  | 2020-06-21 16:30 | 2020-06-22 17:30 | 1.0417 | Complete
| Functional Requirements Specification |  | taher |  | 2020-06-22 17:30 | 2020-06-23 23:30 | 1.25 | Complete
| User Characteristics |  | taher |  | 2020-06-23 23:30 | 2020-06-24 11:30 | 0.5 | Complete
| Non-Functional Requirements |  | taher |  | 2020-06-24 11:30 | 2022-10-02 | 829.5208 | Complete
| Requirements Specification |  | kamel |  | 2020-06-21 15:00 | 2020-06-21 16:30 | 0.0625 | Complete
| External Interface Requirements |  | kamel |  | 2020-06-21 15:00 | 2020-06-21 15:15 | 0.010417 | Complete
| Functional Requirements Specification |  | kamel |  | 2020-06-21 15:15 | 2020-06-21 15:45 | 0.020833 | Complete
| Detailed Non-Functional Requirement |  | kamel |  | 2020-06-21 15:45 | 2020-06-24 22:30 | 3.2812 | Complete

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.